## Summary
Project Name	:	Demand Note Automation Software of BTRC
Test Developed by	:	Smaranika Sarker
Test Case Preparation Date	:	4/2/2024
Version	:	0.1

Total scenarios	:	TS-40
Total Test case	:	TC-356
Test case with steps	:

Total Passed test case	:	TC-340
Total Failed test case	:	TC-12
Total blocked test case	:
Total untested	:
Total	:	0

## Test_Scenarios
Test Scenario No.	User Type	Module	SubModule	Sub-Submodule	Sub-Sub-Submodule	Test Scenario	TC	POC	Priority	Planned Execution Date	Actual Execution Date
TS001	Login	Demand Note Automation Management System	BTRC Login			BTRC Login
TS002			Company Login			Company Login
TS003	Admin		Dashboard			Dashboard	9		High
TS004			Users			User List	11		High
TS005						Add New User	4		High
TS006			Settings	Services		Services List	11		High
TS007						Add Services	4		High
TS008				Institutes		Institutes List	14		High
TS009						Add Institutes	5		High
TS010				Departments		Departments List	11		High
TS011						Add Departments	4		High
TS012				Designations		Designations list	11		High
TS013						Add Designations	4		High
TS014				Frequency Bands		Frequency Bands list	13		High
TS015						Add Frequency Bands	4		High
TS016				Frequency Charges		Frequency Charges list	11		High
TS017						Add Frequency Charges	4		High
TS018				Power Output Charges		Power Output Charges List	13		High
TS019						Add Power Output Charges	4		High
TS020				Terminal Charges		Terminal Charges list	11		High
TS021						Add Terminal Charges	4		High
TS022				Miscellaneous Charges		Miscellaneous Charges list	11		High
TS023						Add Miscellaneous Charges	4		High
TS024				Licence Fee		Licence Fee List	11		High
TS025						Add Licence Fee	4		High
TS026				Groups		Group Records	13		High
TS027						Add Groups	4		High
TS028				Wings		Wings list	14		High
TS029						Add Wings	5		High
TS030				Service Mapping		Service Mapping list	13		High
TS031						Add Service Mapping	3		High
TS032			Application			Application List	41		High
TS033						Add Application	5		High
TS034			Demand Notes	Demand Notes		Demand Notes	20		High
TS035			Reports	Category Wise DNs		Category Wise DNs	12		High
TS036				Charge Expire DNs		Charge Expire DNs
TS037				Push Notification		Push Notification
TS038				Radio Eqipments		Radio Eqipments
TS039	Company		Dashboard			Company Dashboard
TS040			logout			Logout

## Test_cases
Test Case Number	Test Case Name/Title	Description	Expected Result	Actual Result	Category	Test results	Defect ID	Defect Severity	Comments	Test Data	Planned Execution Date	Actual Execution Date	Firefox	Chrome	IE	Edge	Executed By	Browser Execution By
TS001_TC001	BTRC Login Button	Redirect to Admin login page	It should work	it works properly	Functional	Pass
TS001_TC002	Login Page Input Field	Redirect to Admin Homepage	It should work	it works properly	Functional	Pass
TS001_TC003	Admin Login page Login Button	It should work	It should work	it works properly	Functional	Pass
TS001_TC004	Login page Forgot Password Button	It should work	It should work	it works properly	Functional	Pass
TS002_TC001	Company Login Button	Redirect to Company login page	It should work	it works properly	Functional	Pass
TS002_TC002	Login Page Input Field	It should work	It should work	it works properly	Functional	Pass
TS002_TC003	Login page Forgot Password Button	It should work	It should work	it works properly	Functional	Pass
TS002_TC004	Company Login page Log in Button	Redirect to Company Homepage	It should work	it works properly	Functional	Pass
TS003_TC001	Notification Box	It should work	It should work	it works properly	Functional	Pass
TS003_TC002	Admin Logout			it works properly	Functional	Pass
TS003_TC003	Pending Verification Demand Notes Table Show / entries Functionality		It should work	it works properly	Functional	Pass
TS003_TC004	Search Option		It should work	it works properly	Functional	Pass
TS003_TC005	Pending Verification Demand Notes Table Sorting Functionality From Table Heading		It should work	it works properly	Functional	Pass
TS003_TC006	Pending Verification Demand Notes Table Action column View Button		It should work	it works properly	Functional	Pass
TS003_TC007	View Page Verify Button		It should work	it works properly	Functional	Pass
TS003_TC008	View Page Print Button		It should work	it works properly	Functional	Pass
TS003_TC009	Pending Verification Demand Notes Table Action column Send to e nothi Button		It should work	it works properly	Functional	Pass
TS004_TC001	Add User Button		It should work	it works properly	Functional	Pass
TS004_TC002	User List Table Show / entries Functionality		It should work	it works properly	Functional	Pass
TS004_TC003	Search Option		It should work	it works properly	Functional	Pass
TS004_TC004	User List Table Sorting Functionality From Table Heading		It should work	it works properly	Functional	Pass
TS004_TC005	User List Table Action column Edit Button		It should work	it works properly	Functional	Pass
TS004_TC006	Edit user Page: Text Input fields		It should work	showing invalid Contact number / with country code.	Functional	Fail		Enhancement	1. showing invalid Contact number / with country code.
TS004_TC007	Edit user Page: Dropdown Input fields		It should work	it works properly	Functional	Pass
TS004_TC008	Edit user Page: Save Button		It should work	it works properly	Functional	Pass
TS004_TC009	Edit user Page: View All Button		It should work	it works properly	Functional	Pass
TS004_TC010	User List Table Action column Delete Button		It should work	It works properly	Functional	Pass
TS004_TC011	Page Changing Option		It should work	it works	Functional	Pass
TS005_TC001	Add User: Text Input fields		It should work	showing invalid Contact number / with country code.	Functional	Fail		Enhancement	showing invalid Contact number / with country code.
TS005_TC002	Dropdown Input fields		It should work	it works	Functional	Pass
TS005_TC003	Save Button		It should work	it works	Functional	Pass
TS005_TC004	View All Button		It should work	it works	Functional	Pass
TS006_TC001	Add Service Button	Shoud work Properly	It should work	Working properly	Functional	Pass
TS006_TC002	Service List Table Show / entries Functionality	Shoud work Properly	It should work	Working properly	Functional	Pass
TS006_TC003	Search Option	it should Search	It should work	Working properly	Functional	Pass
TS006_TC004	Service List Table Sorting Functionality From Table Heading	it should Sorting table data	It should work	working properly	Functional	Pass
TS006_TC005	Service List Table Action column Edit Button	Shoud work Properly	It should work	working properly	Functional	Pass
TS006_TC006	Edit Service Page: Text Input fields	Shoud work Properly	It should work		Functional	Pass
TS006_TC007	Edit Service Page: Dropdown Input fields	Shoud work Properly	It should work	working properly	Functional	Pass
TS006_TC008	Edit user Page: Update Service Button	Should Update Informations	It should work	working properly	Functional	Pass
TS006_TC009	Edit user Page: Service list Button	Shoud work Properly	It should work	working properly	Functional	Pass
TS006_TC010	Service List Table Action column Delete Button	it should delete	It should work	working properly	Functional	Pass
TS006_TC011	Page Changing Option	Chnaging pages of the table	It should work	working properly	Functional	Pass
TS007_TC001	Add Service Page Text Input fields	Shoud work Properly	It should work		Functional	Pass
TS007_TC002	Dropdown Input fields	Shoud work Properly	It should work	it works	Functional	Pass
TS007_TC003	Add Service Button	Shoud work Properly	It should work	it works	Functional	Pass
TS007_TC004	Service list Button	Shoud work Properly	It should work	it works	Functional	Pass
TS008_TC001	Add Institute Button	Shoud work Properly	It should work	it works	Functional	Pass
TS008_TC002	Institutes List Table Show / entries Functionality	Shoud work Properly	It should work	it works	Functional	Pass
TS008_TC003	Search Option	Shoud work Properly	It should work	it works	Functional	Pass
TS008_TC004	Institutes List Table Sorting Functionality From Table Heading	Shoud work Properly	It should work	it works	Functional	Pass
TS008_TC005	Institutes List Table Action column View Button	Shoud work Properly	It should work	it works	Functional	Pass
TS008_TC006	View Institutes Page: Institutes List Button		It should work	it works	Functional	Pass
TS008_TC007	Institutes List Table Action column Edit Button		It should work	it works	Functional	Pass
TS008_TC008	Edit Institutes Page: Text Input fields		It should work	1. Password fields is not mandatory / 2. showing invalid Contact number / with country code.	Functional	Fail		Minor	1. Password fields is not mandatory / 2.showing invalid Contact number / with country code.	.
TS008_TC009	Edit Institutes Page: Dropdown Input fields		It should work	it works	Functional	Pass
TS008_TC010	Edit Institutes Page: Add Attachments Input field		It should work	it works	Functional	Pass
TS008_TC011	Edit Institutes Page: Update Institutes Button		It should work	it works	Functional	Pass
TS008_TC012	Edit Institutes Page: Institutes list Button		It should work	it works	Functional	Pass
TS008_TC013	Institutes List Table Action column Delete Button		It should work	it works	Functional	Pass
TS008_TC014	Page Changing Option		It should work	it works	Functional	Pass
TS009_TC001	Add Institutes Page: Text Input fields		It should work	1. showing invalid Contact number / with country code.	Functional	Fail		Enhancement	1.showing invalid Contact number / with country code.
TS009_TC002	Dropdown Input fields		It should work	it works	Functional	Pass
TS009_TC003	Add Attachments Input field		It should work	it works	Functional	Pass
TS009_TC004	Add Institute Button		It should work	it works	Functional	Pass
TS009_TC005	Institutes list Button		It should work	it works	Functional	Pass
TS010_TC001	Add Department Button		It should work	it works	Functional	Pass
TS010_TC002	Department List Table Show / entries Functionality		It should work	it works	Functional	Pass
TS010_TC003	Search Option		It should work	it works	Functional	Pass
TS010_TC004	Department List Table Sorting Functionality From Table Heading		It should work	it works	Functional	Pass
TS010_TC005	Department List Table Action column Edit Button		It should work	it works	Functional	Pass
TS010_TC006	Edit Department Page: Text Input fields		It should work	.	Functional	Pass		Minor
TS010_TC007	Edit Department Page: Dropdown Input fields		It should work	it works	Functional	Pass
TS010_TC008	Edit Department Page: Update Department Button		It should work	it works	Functional	Pass
TS010_TC009	Edit Department Page:Department list Button		It should work	it works	Functional	Pass
TS010_TC010	Department List Table Action column Delete Button		It should work	it works	Functional	Pass
TS010_TC011	Page Changing Option		It should work	it works	Functional	Pass
TS011_TC001	Add Department Page: Text Input fields		It should work		Functional	Pass		Minor	.	.
TS011_TC002	Dropdown Input fields		It should work	it works	Functional	Pass
TS011_TC003	Add Department Button		It should work	it works	Functional	Pass
TS011_TC004	Department list Button		It should work	it works	Functional	Pass
TS012_TC001	Add Designation Button		It should work	it works	Functional	Pass
TS012_TC002	Designation List Table Show / entries Functionality		It should work	it works	Functional	Pass
TS012_TC003	Search Option		It should work	it works	Functional	Pass
TS012_TC004	Designation List Table Sorting Functionality From Table Heading		It should work	it works	Functional	Pass
TS012_TC005	Designation List Table Action column Edit Button		It should work	it works	Functional	Pass
TS012_TC006	Edit Designation Page: Text Input fields		It should work		Functional	Pass		Minor
TS012_TC007	Edit Designation Page: Dropdown Input fields		It should work	it works	Functional	Pass
TS012_TC008	Edit Designationt Page: Update Designation Button		It should work	it works	Functional	Pass
TS012_TC009	Edit Designation Page:Designation list Button		It should work	it works	Functional	Pass
TS012_TC010	Designation List Table Action column Delete Button		It should work	it works	Functional	Pass
TS012_TC011	Page Changing Option		It should work	it works	Functional	Pass
TS013_TC001	Add Designation Page: Text Input fields		It should work		Functional	Pass		Minor
TS013_TC002	Dropdown Input fields		It should work	working properly	Functional	Pass
TS013_TC003	Add Designation Button		It should work	working properly	Functional	Pass
TS013_TC004	Designation list Button		It should work	working properly	Functional	Pass
TS014_TC001	Add Frequency Band Button		It should work	working properly	Functional	Pass
TS014_TC002	Frequency Band List Table Show / entries Functionality		It should work	Working Properly	Functional	Pass
TS014_TC003	Search Option		It should work	Working Properly	Functional	Pass
TS014_TC004	Frequency Band List Table Sorting Functionality From Table Heading		It should work	Working Properly	Functional	Pass
TS014_TC005	Frequency Band List Table Action column Edit Button		It should work	Working Properly	Functional	Pass
TS014_TC006	EditFrequency Band Page: Text Input fields		It should work	.	Functional	Pass		Minor	.	.
TS014_TC007	Edit Frequency Band Page: Dropdown Input fields		It should work	Working Properly	Functional	Pass
TS014_TC008	Edit Frequency Band Page: Update Frequency Band Button		It should work	Working Properly	Functional	Pass
TS014_TC009	Edit Frequency Band Page:Frequency Band list Button		It should work	Working Properly	Functional	Pass
TS014_TC010	Frequency Band List Table Action column Delete Button		It should work	Working Properly	Functional	Pass
TS014_TC011	Delete Conformation Yes button		It should work	Working Properly	Functional	Pass
TS014_TC012	Delete Conformation No button		It should work	Working Properly	Functional	Pass
TS014_TC013	Page Changing Option		It should work	Working Properly	Functional	Pass
TS015_TC001	Add Frequency Band Page: Text Input fields		It should work		Functional	Pass		Minor	.	.
TS015_TC002	Dropdown Input fields		It should work	Working properly	Functional	Pass
TS015_TC003	Add Frequency Band Button		It should work	Working properly	Functional	Pass
TS015_TC004	Frequency Band list Button		It should work	Working properly	Functional	Pass
TS016_TC001	Add Frequency Charge Button		It should work	Working properly	Functional	Pass
TS016_TC002	Frequency Charge List Table Show / entries Functionality		It should work	Working properly	Functional	Pass
TS016_TC003	Search Option		It should work	Working properly	Functional	Pass
TS016_TC004	Frequency Charge List Table Sorting Functionality From Table Heading		It should work	Working properly	Functional	Pass
TS016_TC005	Frequency Charge List Table Action column Edit Button		It should work	Working properly	Functional	Pass
TS016_TC006	Edit Frequency Charge Page: Text Input fields		It should work	1. Frequency Charge input field is Taking / characters as input	Functional	Fail		Enhancement	Frequency Charge input field is Taking / characters as input	Tested data is Character ( Character Input )
TS016_TC007	Edit Frequency Charge Page: Dropdown Input fields		It should work	Working properly	Functional	Pass
TS016_TC008	Edit Frequency Charge Page: Update Frequency Charge Button		It should work	Working properly	Functional	Pass
TS016_TC009	Edit Frequency Charge Page:Frequency Charge list Button		It should work	Working properly	Functional	Pass
TS016_TC010	Frequency Charge List Table Action column Delete Button		It should work	Working properly	Functional	Pass
TS016_TC011	Page Changing Option		It should work	Working properly	Functional	Pass
TS017_TC001	Add Frequency Charge Page: Text Input fields		It should work	1.Frequency Charge input field is Taking / characters as input	Functional	Fail		Enhancement	1.Frequency Charge input field is Taking / characters as input	Tested data is Character ( Character Input )
TS017_TC002	Dropdown Input fields		It should work	Working properly	Functional	Pass
TS017_TC003	Add Frequency Charge Button		It should work	Working properly	Functional	Pass
TS017_TC004	Frequency Charges list Button		It should work	Working properly	Functional	Pass
TS018_TC001	Add Power Output Charge Button		It should work	Working properly	Functional	Pass
TS018_TC002	Power Output Charge List Table Show / entries Functionality		It should work	Working properly	Functional	Pass
TS018_TC003	Search Option		It should work	Working properly	Functional	Pass
TS018_TC004	Power Output Charge List Table Sorting Functionality From Table Heading		It should work	Working properly	Functional	Pass
TS018_TC005	Power Output Charge List Table Action column Edit Button		It should work	Working properly	Functional	Pass
TS018_TC006	Edit Power Output Charge Page: Text Input fields		It should work	1.Power Output Charge input field is Taking / characters as input / 2.Power Output is taking unlimited Data, but SRS Mentioned Only 255Number.	Functional	Fail		Enhancement	1.Power Output Charge input field is Taking / characters as input / 2.Power Output is taking unlimited Data, but SRS Mentioned Only 255Number.
TS018_TC007	Edit Power Output Charge Page: Dropdown Input fields		It should work	Working properly	Functional	Pass
TS018_TC008	Edit Power Output Charge Page: Update Power Output Charge Button		It should work	Working properly	Functional	Pass
TS018_TC009	Edit Power Output Charge Page:Power Output Charge list Button		It should work	Working properly	Functional	Pass
TS018_TC010	Power Output Charge List Table Action column Delete Button		It should work	Working properly	Functional	Pass
TS018_TC011	Delete Confirmattion Yes Button		It should work	Working properly	Functional	Pass
TS018_TC012	Delete Confirmattion No Button		It should work	Working properly	Functional	Pass
TS018_TC013	Page Changing Option		It should work	Working properly	Functional	Pass
TS019_TC001	Add Power Output Charge Band Page: Text Input fields		It should work	1.Power Output Charge input field is Taking / characters as input / 2.Power Output is taking unlimited Data, but SRS Mentioned Only 255Number.	Functional	Fail		Enhancement	1.Power Output Charge input field is Taking / characters as input / 2.Power Output is taking unlimited Data, but SRS Mentioned Only 255Number.
TS019_TC002	Dropdown Input fields		It should work	Working properly	Functional	Pass
TS019_TC003	Add Power Output Charge Button		It should work	Working properly	Functional	Pass
TS019_TC004	Power Output Charges list Button		It should work	Working properly	Functional	Pass
TS020_TC001	Add Terminal Charge Button		It should work	Working properly	Functional	Pass
TS020_TC002	Terminal Charge List Table Show / entries Functionality		It should work	Working properly	Functional	Pass
TS020_TC003	Search Option		It should work	Working properly	Functional	Pass
TS020_TC004	Terminal Charge List Table Sorting Functionality From Table Heading		It should work	Working properly	Functional	Pass
TS020_TC005	Terminal Charge List Table Action column Edit Button		It should work	Working properly	Functional	Pass
TS020_TC006	EditTerminal Charge Page: Text Input fields		It should work	1.Terminal Charge amount is taking / characters as input / 2.Terminal Charge input fields is taking unlimited Data.	Functional	Fail		Enhancement	1.Terminal Charge amount is taking / characters as input / 2.Terminal Charge input fields is taking unlimited Data.
TS020_TC007	Edit Terminal Charge Page: Dropdown Input fields		It should work	Working properly	Functional	Pass
TS020_TC008	Edit Terminal Charge Page: Update Terminal Charge Button		It should work	Working properly	Functional	Pass
TS020_TC009	Edit Terminal Charge Page:Terminal Charge list Button		It should work	Working properly	Functional	Pass
TS020_TC010	Terminal Charge List Table Action column Delete Button		It should work	Working properly	Functional	Pass
TS020_TC011	Page Changing Option		It should work	Working properly	Functional	Pass
TS021_TC001	Add Terminal Charge Band Page: Text Input fields		It should work	1.Terminal Charge amount is taking / characters as input / 2.Terminal Charge input fields is taking unlimited Data.	Functional	Fail		Enhancement	1.Terminal Charge amount is taking / characters as input / 2.Terminal Charge input fields is taking unlimited Data.
TS021_TC002	Dropdown Input fields		It should work	Working properly	Functional	Pass
TS021_TC003	Add Terminal Charge Button		It should work	Working properly	Functional	Pass
TS021_TC004	Terminal Charge list Button		It should work	Working properly	Functional	Pass
TS022_TC001	Add Miscellaneous Charge Button		It should work	Working properly	Functional	Pass
TS022_TC002	Miscellaneous Charge List Table Show / entries Functionality		It should work	Working properly	Functional	Pass
TS022_TC003	Search Option		It should work	Working properly	Functional	Pass
TS022_TC004	Miscellaneous Charge List Table Sorting Functionality From Table Heading		It should work	Working properly	Functional	Pass
TS022_TC005	Miscellaneous Charge List Table Action column Edit Button		It should work	Working properly	Functional	Pass
TS022_TC006	Edit Miscellaneous Charge Page: Text Input fields		It should work	1.Miscellaneous Charge amount field is Taking / characters as input / 2.Miscellaneous charge input fields is taking unlimited Data	Functional	Fail		Enhancement	1.Miscellaneous Charge amount field is Taking / characters as input / 2.Miscellaneous charge input fields is taking unlimited Data
TS022_TC007	Edit Miscellaneous Charge Page: Dropdown Input fields		It should work	Working properly	Functional	Pass
TS022_TC008	Edit Miscellaneous Charge Page: Update Miscellaneous Charge Button		It should work	Working properly	Functional	Pass
TS022_TC009	Edit Miscellaneous Charge Page:Miscellaneous Charge list Button		It should work	Working properly	Functional	Pass
TS022_TC010	Miscellaneous Charge List Table Action column Delete Button		It should work	Working properly	Functional	Pass
TS022_TC011	Page Changing Option		It should work	Working properly	Functional	Pass
TS023_TC001	Add Miscellaneous Charge Band Page: Text Input fields		It should work	1.Miscellaneous Charge amount field is Taking / characters as input / 2.Miscellaneous charge input fields is taking unlimited Data	Functional	Fail		Enhancement	1.Miscellaneous Charge amount field is Taking / characters as input / 2.Miscellaneous charge input fields is taking unlimited Data
TS023_TC002	Dropdown Input fields		It should work	Working properly	Functional	Pass
TS023_TC003	Add Miscellaneous Charge Button		It should work	Working properly	Functional	Pass
TS023_TC004	Miscellaneous Charge list Button		It should work	Working properly	Functional	Pass
TS024_TC001	Add Licence Fee Button		It should work	Working properly	Functional	Pass
TS024_TC002	Licence Fee List Table Show / entries Functionality		It should work	Working properly	Functional	Pass
TS024_TC003	Search Option		It should work	Working properly	Functional	Pass
TS024_TC004	Licence Fee List Table Sorting Functionality From Table Heading		It should work	Working properly	Functional	Pass
TS024_TC005	Licence Fee List Table Action column Edit Button		It should work	Working properly	Functional	Pass
TS024_TC006	Edit Licence Fee Page: Text Input fields		It should work	1. Licence Fee Text is taking unlimited Data / 2. Licence Fee Amount filed Input characters	Functional	Fail		Enhancement	1. Licence Fee Text is taking unlimited Data / 2. Licence Fee Amount filed Input characters
TS024_TC007	Edit Licence Fee Page: Dropdown Input fields		It should work	Working properly	Functional	Pass
TS024_TC008	Edit Licence Fee Page: Update Licence Fee Button		It should work	Working properly	Functional	Pass
TS024_TC009	Edit Licence Fee Page:Licence Fee list Button		It should work	Working properly	Functional	Pass
TS024_TC010	Licence Fee List Table Action column Delete Button		It should work	Working properly	Functional	Pass
TS024_TC011	Page Changing Option		It should work	Working properly	Functional	Pass
TS025_TC001	Add Licence Fee Band Page: Text Input fields		It should work	1. Licence Fee Text is taking unlimited Data / 2. Licence Fee Amount filed Input characters	Functional	Fail		Enhancement	1. Licence Fee Text is taking unlimited Data / 2. Licence Fee Amount filed Input characters
TS025_TC002	Dropdown Input fields		It should work	Working Properly	Functional	Pass
TS025_TC003	Add Licence Fee Button		It should work	Working Properly	Functional	Pass
TS025_TC004	Licence Fee list Button		It should work	Working Properly	Functional	Pass
TS026_TC001	Add New Button		It should work	It works Perfectly	Functional	Pass
TS026_TC002	Group Records List Table Show / entries Functionality		It should work	It works Perfectly	Functional	Pass
TS026_TC003	Search Option		It should work	It works Perfectly	Functional	Pass
TS026_TC004	Group Records List Table Sorting Functionality From Table Heading		It should work	It works Perfectly	Functional	Pass
TS026_TC005	Group Records List Table Action column Edit Button		It should work	It works Perfectly	Functional	Pass
TS026_TC006	Edit Group Records Page: Text Input fields		It should work	.	Functional	Pass		Minor	.
TS026_TC007	Edit Group Records Page: Permission Check boxes		It should work	Working properly	Functional	Pass
TS026_TC008	Edit Group Records Page: Save Button		It should work	Working properly	Functional	Pass
TS026_TC009	Edit Group Records Page:View All Button		It should work	Working properly	Functional	Pass
TS026_TC010	Group Records List Table Action column Delete Button		It should work	Working properly	Functional	Pass
TS026_TC011	Delete Popup Confirmation Message Yes Button	To confirm delete the status	Should work properly	Working properly	Functional	Pass
TS026_TC012	Delete Popup Confirmation Message No Button	To cencle delete the status	Should work properly	Working properly	Functional	Pass
TS026_TC013	Page Changing Option		It should work	Working properly	Functional	Pass
TS027_TC001	Add Group Records Page: Text Input fields		It should work	.	Functional	Pass		Minor	Group name field input "@$%@" characters
TS027_TC002	Permission Check boxes		It should work	Working properly	Functional	Pass
TS027_TC003	Save Button		It should work	Working properly	Functional	Pass
TS027_TC004	View All Button		It should work	Working properly	Functional	Pass
TS028_TC001	Add New Button		It should work	Working properly	Functional	Pass
TS028_TC002	Wing Records List Table Show / entries Functionality		It should work	Working properly	Functional	Pass
TS028_TC003	Search Option		It should work	Working properly	Functional	Pass
TS028_TC004	Wing Records List Table Sorting Functionality From Table Heading		It should work	Working properly	Functional	Pass
TS028_TC005	Wing Records List Table Action column Edit Button		It should work	Working properly	Functional	Pass
TS028_TC006	Edit Wing Records Page: Text Input fields		It should work	.	Functional	Pass		Minor	Wing name field input special characters like just "@"
TS028_TC007	Edit Wing Records Page: Dropdown Input field		It should work	Working properly	Functional	Pass
TS028_TC008	Edit Wing Records Page: Remove list button		It should work	Working properly	Functional	Pass
TS028_TC009	Edit Wing Records Page: Save Button		It should work	Working properly	Functional	Pass
TS028_TC010	Edit Wing Records Page:View All Button		It should work	Working properly	Functional	Pass
TS028_TC011	Wing Records List Table Action column Delete Button		It should work	Working properly	Functional	Pass
TS028_TC012	Delete Popup Confirmation Message Yes Button	To confirm delete the status	Should work properly	Working properly	Functional	Pass
TS028_TC013	Delete Popup Confirmation Message No Button	To cencle delete the status	Should work properly	Working properly	Functional	Pass
TS028_TC014	Page Changing Option		It should work	Working properly	Functional	Pass
TS029_TC001	Add Wing Records Page: Text Input fields		It should work	.	Functional	Pass		Minor	Wing name field input special characters like just "(())"
TS029_TC002	Dropdown Input field		It should work	Working properly	Functional	Pass
TS029_TC003	Remove list button		It should work	Working properly	Functional	Pass
TS029_TC004	Save Button		It should work	Working properly	Functional	Pass
TS029_TC005	View All Button		It should work	Working properly	Functional	Pass
TS030_TC001	Add New Button		It should work	Working properly	Functional	Pass
TS030_TC002	Service Mapping List Table Show / entries Functionality		It should work	Working properly	Functional	Pass
TS030_TC003	Search Option		It should work	Working properly	Functional	Pass
TS030_TC004	Service Mapping List Table Sorting Functionality From Table Heading		It should work	Working properly	Functional	Pass
TS030_TC005	Service Mapping List Table Action column Edit Button		It should work	Working properly	Functional	Pass
TS030_TC006	Edit Service MappingPage: Text Input fields		It should work	Working properly	Functional	Pass
TS030_TC007	Edit Service Mapping Page: Dropdown Input field		It should work	Working properly	Functional	Pass
TS030_TC008	Edit Service Mapping Page: Save Button		It should work	Working properly	Functional	Pass
TS030_TC009	Edit Service Mapping Page:View All Button		It should work	Working properly	Functional	Pass
TS030_TC010	Service Mapping List Table Action column Delete Button		It should work	Working properly	Functional	Pass
TS030_TC011	Delete Popup Confirmation Message Yes Button	To confirm delete the status	Should work properly	Working properly	Functional	Pass
TS030_TC012	Delete Popup Confirmation Message No Button	To cencle delete the status	Should work properly	Working properly	Functional	Pass
TS030_TC013	Page Changing Option		It should work	Working properly	Functional	Pass
TS031_TC001	Dropdown Input field		It should work	Working properly	Functional	Pass
TS031_TC002	Save Button		It should work	Working properly	Functional	Pass
TS031_TC003	View All Button		It should work	Working properly	Functional	Pass
TS032_TC001	Add Application Button		It should work	Working properly	Functional	Pass
TS032_TC002	Application List Table Show / entries Functionality		It should work	Working properly	Functional	Pass
TS032_TC003	Search Option		It should work	Working properly	Functional	Pass
TS032_TC004	Application List Table Sorting Functionality From Table Heading		It should work	Working properly	Functional	Pass
TS032_TC005	Application List Table Action column Generate Demand Notes Button		It should work	Working properly	Functional	Pass
TS032_TC006	Generate Demand Notes Page: Text Input fields		It should work	Working properly	Functional	Pass
TS032_TC007	Generate Demand Notes Page: Generate Button		It should work	Working properly	Functional	Pass
TS032_TC008	Generate-Demand-Note Popup Message: Generate View: Print Button	To print the page	Should work properly	Working properly	Functional	Pass
TS032_TC009	Generate-Demand-Note Popup Message: Generate View: Verify Button	To verify the page information	Should work properly	Working properly	Functional	Pass
TS032_TC010	Application List Table Action column Siblings Application Button		It should work	Working properly	Functional	Pass
TS032_TC011	Application List Button		It should work	Working properly	Functional	Pass
TS032_TC012	Siblings Application List Table Show / entries Functionality		It should work	Working properly	Functional	Pass
TS032_TC013	Search Option		It should work	Working properly	Functional	Pass
TS032_TC014	Siblings Application List Table Sorting Functionality From Table Heading		It should work	Working properly	Functional	Pass
TS032_TC015	Siblings Application List Table Action column Generate Demand Notes Button		It should work	Working properly	Functional	Pass
TS032_TC016	Siblings Application List Table Action column View Button		It should work	Working properly	Functional	Pass
TS032_TC017	View Page Application List Button		It should work	Working properly	Functional	Pass
TS032_TC018	Siblings Application List Table Action column Edit Button		It should work	Working properly	Functional	Pass
TS032_TC019	Edit Page All Input Field		It should work	Working properly	Functional	Pass
TS032_TC020	Add File option		It should work	Working properly	Functional	Pass
TS032_TC021	Update Application Button			Working properly	Functional	Pass
TS032_TC022	Siblings Application List Table Action column Delete Button		It should work	Working properly	Functional	Pass
TS032_TC023	Page Changing Option		It should work	Working properly	Functional	Pass
TS032_TC024	Application List Table Action column Update Application Button		It should work	Working properly	Functional	Pass
TS032_TC025	Update Application Page: Text Input fields		It should work		Functional	Pass
TS032_TC026	Dropdown Input field		It should work	its works	Functional	Pass
TS032_TC027	Upload Attachment option		It should work	its works	Functional	Pass
TS032_TC028	Add Row Button		It should work	its works	Functional	Pass
TS032_TC029	Delete Row Button		It should work	its works	Functional	Pass
TS032_TC030	Update Application Button		It should work	its works	Functional	Pass
TS032_TC031	Application List Button		It should work	its works	Functional	Pass
TS032_TC032	Application List Table Action column View Button		It should work	its works	Functional	Pass
TS032_TC033	View Application Page Application List Button		It should work	its works	Functional	Pass
TS032_TC034	Application List Table Action column Edit Button		It should work	its works	Functional	Pass
TS032_TC035	Edit Application Page: Text Input fields		It should work		Functional	Pass
TS032_TC036	Dropdown Input field		It should work	working properly	Functional	Pass
TS032_TC037	Upload Attachment option		It should work	working properly	Functional	Pass
TS032_TC038	Update Application Button		It should work	working properly	Functional	Pass
TS032_TC039	Application List Button		It should work	working properly	Functional	Pass
TS032_TC040	Application List Table Action column Delete Button		It should work	working properly	Functional	Pass
TS032_TC041	Application List Page Changing Option		It should work	working properly	Functional	Pass
TS033_TC001	Add Application Page: Text Input fields		It should work		Functional	Pass
TS033_TC002	Dropdown Input field		It should work	working properly	Functional	Pass
TS033_TC003	Upload Attachment option		It should work	working properly	Functional	Pass
TS033_TC004	add Application Button		It should work	working properly	Functional	Pass
TS033_TC005	Application List Button		It should work	working properly	Functional	Pass
TS034_TC001	Demand Notes List Table Show / entries Functionality		It should work	it works properly	Functional	Pass
TS034_TC002	Search Option		It should work	it works properly	Functional	Pass
TS034_TC003	Demand Notes List Table Sorting Functionality From Table Heading		It should work	it works properly	Functional	Pass
TS034_TC004	Demand Notes Table Action column Details Button		It should work	it works properly	Functional	Pass
TS034_TC005	Demand Notes Table Action column Record No Button		It should work	it works properly	Functional	Pass
TS034_TC006	Record No page Input Fields Functionality		It should work		Functional	Pass
TS034_TC007	Record No page Save Button		It should work	Working properly	Functional	Pass
TS034_TC008	Demand Notes Table Action column Due Button		It should work	Working properly	Functional	Pass
TS034_TC009	Due page Input Fields Functionality		It should work	Working properly	Functional	Pass
TS034_TC010	Due page Save Button		It should work	Working properly	Functional	Pass
TS034_TC011	Demand Notes Table Action column Pay Button		It should work	Working properly	Functional	Pass
TS034_TC012	Pay page Input Fields Functionality		It should work	Working properly	Functional	Pass
TS034_TC013	Pay page Add Attachment Functionality		It should work	Working properly	Functional	Pass
TS034_TC014	Pay page Save Button		It should work	Working properly	Functional	Pass
TS034_TC015	Demand Notes List Table Action column Doc Button		It should work	Working properly	Functional	Pass
TS034_TC016	Doc page Print Button		It should work		Functional	Pass
TS034_TC017	Demand Notes List Table Action column Send to E-nothi Button		It should work		Functional	Skipped
TS034_TC018	Demand Notes List Table Action column Delete Button		It should work	Working properly	Functional	Pass
TS034_TC019	Delete Confirmation Message box		It should work	Working properly	Functional	Pass
TS034_TC020	Page Changing Option		It should work	Working properly	Functional	Pass
TS035_TC001	Dropdown Input Field		It should work	Working properly	Functional	Pass
TS035_TC002	Search Button		It should work	Working properly	Functional	Pass
TS035_TC003	Category Wise DNs List Table Show / entries Functionality		It should work	Working properly	Functional	Pass
TS035_TC004	Search Option		It should work	Working properly	Functional	Pass
TS035_TC005	Category Wise DNs List Table Sorting Functionality From Table Heading		It should work	Working properly	Functional	Pass
TS035_TC006	Category Wise DNs List Table Action column Details Button		It should work	Working properly	Functional	Pass
TS035_TC007	Details Table Show / entries Functionality		It should work	Working properly	Functional	Pass
TS035_TC008	Details Page : Pdf Button		It should work	Working properly	Functional	Pass
TS035_TC009	Details Page: Excel Button		It should work	Working properly	Functional	Pass
TS035_TC010	Details Page: Search Option		It should work	Working properly	Functional	Pass
TS035_TC011	Details Page: Page Changing Option		It should work	Working properly	Functional	Pass
TS035_TC012	Category Wise DNs Page Changing Option		It should work	Working properly	Functional	Pass
TS036_TC001	Dropdown Input Field		It should work	Working properly	Functional	Pass
TS036_TC002	Search Button		It should work	Working properly	Functional	Pass
TS036_TC003	Charge Expire DNs List Table Show / entries Functionality		It should work	Working properly	Functional	Pass
TS036_TC004	Search Option		It should work	Working properly	Functional	Pass
TS036_TC005	Charge Expire DNs List Table Sorting Functionality From Table Heading		It should work	Working properly	Functional	Pass
TS036_TC006	Charge Expire DNs List Table Action column Details Button		It should work	Working properly	Functional	Pass
TS036_TC007	Details Table Show / entries Functionality		It should work	Working properly	Functional	Pass
TS036_TC008	Details Page : Pdf Button		It should work	Working properly	Functional	Pass
TS036_TC009	Details Page: Excel Button		It should work	Working properly	Functional	Pass
TS036_TC010	Details Page: Search Option		It should work	Working properly	Functional	Pass
TS036_TC011	Details Page Table Action Column Send Sms Button		It should work	Working properly	Functional	Pass
TS036_TC012	Details Page: Page Changing Option		It should work	Working properly	Functional	Pass
TS036_TC013	Charge Expire DNs Page Changing Option		It should work	Working properly	Functional	Pass
TS037_TC001	Dropdown Input Field		It should work	Working properly	Functional	Pass
TS037_TC002	Search Button		It should work	Working properly	Functional	Pass
TS037_TC003	Push Notification List Table Show / entries Functionality		It should work	Working properly	Functional	Pass
TS037_TC004	Search Option		It should work	Working properly	Functional	Pass
TS037_TC005	Push Notification List Table Sorting Functionality From Table Heading		It should work	Working properly	Functional	Pass
TS037_TC006	Page Changing Option		It should work	Working properly	Functional	Pass
TS038_TC001	Dropdown Input Field		It should work	Working properly	Functional	Pass
TS038_TC002	Search Button		It should work	Working properly	Functional	Pass
TS038_TC003	Create Pdf Button		It should work	Working properly	Functional	Pass
TS038_TC004	Create Excel Button		It should work	Working properly	Functional	Pass
TS038_TC005	Radio Eqipments List Table Show / entries Functionality		It should work	Working properly	Functional	Pass
TS038_TC006	Search Option		It should work	Working properly	Functional	Pass
TS038_TC007	Radio Eqipments Table Sorting Functionality From Table Heading		It should work	Working properly	Functional	Pass
TS038_TC008	Page Changing Option		It should work	Working properly	Functional	Pass
TS039_TC001	Dashboard Demand Note table Availabality		It should work	Working properly	Functional	Pass
TS039_TC002	Demand Notes List Table Show / entries Functionality		It should work	Working properly	Functional	Pass
TS039_TC003	Search Option		It should work	Working properly	Functional	Pass
TS039_TC004	Demand Notes List Table Sorting Functionality From Table Heading		It should work	Working properly	Functional	Pass
TS039_TC005	Demand Notes List Table Action column View Button		It should work	Working properly	Functional	Pass
TS039_TC006	View Note Page Print Button		It should work	1. printing format is not working and no document can be printed.	Functional	Fail		Normal	1. printing format is not working and no document can be printed.
TS039_TC007	Viwe Note Page Verify Button		It should work	Working properly	Functional	Pass
TS039_TC008	Demand Notes List Page Changing Option		It should work	Working properly	Functional	Pass
TS040_TC001	Logout		It should work	Working properly	Functional	Pass

## Defect-In-BugZilla
Bug ID	Component	Severity	Status	Resolution	Summary	Actual Result	Expected Result	Steps To Reproduce	TC No.	Defect No.	Attachment
	Admin	Enhancement			Demand Note Automation || Login as Admin|| Dashboard|| / User || edit User || contact number is not working	showing invalid Contact number / with country code.	It should work	Go to "http://202.191.121.20/devtest/btrc" / 1. Log in as admin / 2. Go to user page / 3. Click on edit user page form action coloumn / 4. Enter Contact number showing invalid / with country code.	TS004_TC006
	Admin	Enhancement			Demand Note Automantion || Login as Admin || Users || Add User || contact number is not working properly	showing invalid Contact number / with country code.	It should work	Go to "http://202.191.121.20/devtest/btrc" / 1. Log in as admin / 2. Go to users page / 3. Click on add user button / 4. Enter Contact number showing invalid / with country code.	TS005_TC001
	Admin	Minor			Demand Note Automantion || Login as Admin||Settings || institute || edit institute || Contact number & password is not working properly	1. Password fields is not mandatory / 2. showing invalid Contact number / with country code.	It should work	Go to "http://202.191.121.20/devtest/btrc" / 1. Log in as admin / 2. Go to Setting / & Go to institute page / 3. Click on action column edit institute button / 4. Enter Contact number showing invalid / with country code & Password fields is not mandatory / 5. Click on update institute button. Observe the data is getting update.	TC008_TC008
	Admin	Minor			Demand Note Automantion || Login as Admin ||Settings|| institute || add institute || Text input is not working properly	1. showing invalid Contact number / with country code.	It should work	Go to "http://202.191.121.20/devtest/btrc" / 1. Log in as admin / 2. Go to Setting / & Go to institute page / 3. Click on add institute button / 4. Enter Contact number showing invalid / with country code / 5. Click on add institute button. Observe the data is getting added list.	TS009_TC001
	Admin	Enhancement			Demand Note Automantion || Login as Admin || Settings || Freequency Charges || edit Freequency charges from Action column || Frequency Charge input field is Taking / characters as input	1.Frequency Charge input field is Taking / characters as input	It should work	Go to "http://202.191.121.20/devtest/btrc" / 1. Log in as admin / 2. Go to Setting / 2. Frequency Charge page / 3. Click on Edit button from Action Column / 4. Enter "Character data" in Frequency Chargea field / 5. Click on Add freequency button. Observe the data is getting saved.	TS016_TC006
	Admin	Enhancement			Demand Note Automantion || Login as Admin || Settings || Freequency Charges ||Add Freequency charges from Action column || Frequency Charge input field is Taking / characters as input	1.Frequency Charge input field is Taking / characters as input	It should work	Go to "http://202.191.121.20/devtest/btrc" / 1. Log in as admin / 2. Go to Setting / 2. Frequency Charge page / 3. Click on add button / 4. Enter "Character data" in Frequency Chargea field / 5. Click on Add freequency button. Observe the data is getting saved.	TS017_TC001
	Admin	Enhancement			Demand Note Automantion || Login as Admin || Settings || Power Output Charge ||edit Power Output Charge from Action column || Power Output Charge & Power Output / input fields are not working properly	1.Power Output Charge input field is Taking / characters as input / 2.Power Output is taking unlimited Data	It should work	Go to "http://202.191.121.20/devtest/btrc" / 1. Log in as admin / 2. Go to Setting / 2. Power Output Charge / 3. Click on action column edit button / 4. Enter "Character data" in Power Output Charge field & / unlimited data in power output fields / 5. Click on update Power Output charge button. Observe the data is getting saved.	TS018_TC006
	Admin	Enhancement			Demand Note Automation || Login as Admin || Settings || Power Output Charge ||Add Power Output Charge Button || Power Output Charge & Power Output / input fields are not working properly	1.Power Output Charge input field is Taking / characters as input / 2.Power Output is taking unlimited Data, but SRS Mentioned Only 255Number.	It should work	Go to "http://202.191.121.20/devtest/btrc" / 1. Log in as admin / 2. Go to Setting / 2. Power Output Charge / 3. Click on action column edit button / 4. Enter "Character data" in Power Output Charge field & / unlimited data in power output fields / 5. Click on update Power Output charge button. I10Observe the data is getting saved.	TS018_TC006
	Admin	Enhancement			Demand Note Automantion || Login as Admin || Settings || Power Output Charge Band Page || Add Power Output Charge Band Page form action column|| / 1.Power Output Charge input field is Taking / characters as input / 2.Power Output is taking unlimited Data, but SRS Mentioned Only 255Number.	1.Power Output Charge input field is Taking / characters as input / 2.Power Output is taking unlimited Data, but SRS Mentioned Only 255Number.	Should working	Go to "http://202.191.121.20/devtest/btrc" / 1. Log in as admin / 2. Go to Setting / 2. Power Output Charge / 3. Click on action column edit button / 4. Enter "Character data" in Power Output Charge field & / unlimited data in power output fields / 5. Click on update Power Output charge button. I10Observe the data is getting saved.	TS019_TC001
	Admin	Enhancement			Demand Note Automantion || Login as Admin || Settings || Terminal Charges || edit Terminal Charge form action column|| / Terminal Charge amount & Terminal Charge input fields are not working properly .	1.Terminal Charge amount is taking / characters as input / 2.Terminal Charge input fields is taking unlimited Data.	It should work	Go to "http://202.191.121.20/devtest/btrc" / 1. Log in as admin / 2. Go to Setting / & Terminal Charge page / 3. Edit Terminal charge form action column / 4. Enter "Character data" in Terminal charge amount field & / unlimited data in Terminal charge input fields / 5. Click on update Terminal charge button. Observe the data is getting saved.	TS020_TC006
	Admin	Enhancement			Demand Note Automantion || Login as Admin || Settings || Terminal Charges || add Terminal Charge|| / Terminal Charge amount & Terminal Charge input fields are not working properly .	1.Terminal Charge amount is taking / characters as input / 2.Terminal Charge input fields is taking unlimited Data.	It should work	Go to "http://202.191.121.20/devtest/btrc" / 1. Log in as admin / 2. Go to Setting / & Terminal Charge page / 3. Click Add Terminal Charge / 4. Enter "Character data" in Terminal charge amount field & / unlimited data in Terminal charge input fields / 5. Click on addTerminal charge button. Observe the data is getting saved.	TS021_TC001
	Admin	Enhancement			Demand Note Automantion || Login as Admin || Settings || Power Output Charge ||edit Miscellaneous Charge from action column || Miscellaneous Charge / & Miscellaneous Charge amount input fields are not working properly	1.Miscellaneous Charge amount field is Taking / characters as input / 2.Miscellaneous charge input fields is taking unlimited Data	It should work	Go to "http://202.191.121.20/devtest/btrc" / 1. Log in as admin / 2. Go to Setting / 2. Miscellaneous Charges page / 2. Click on edit Miscellaneous Charge button form action column / 3. Enter "Character data" in Miscellaneous Charge amount field & / unlimited data in Miscellaneous Charge input fields / 5. Click on update Miscellaneous Charges button. Observe the data is getting saved.	TS022_TC006
	Admin	Enhancement			Demand Note Automantion || Login as Admin || Settings || Miscellaneous Charges|| add Miscellaneous Charges || Miscellaneous Charge amount & Miscellaneous Charge / input fields are not working properly	1.Miscellaneous Charge amount field is Taking / characters as input / 2.Miscellaneous charge input fields is taking unlimited Data	It should work	Go to "http://202.191.121.20/devtest/btrc" / 1. Log in as admin / 2. Go to Setting / 2. Click on add Miscellaneous Charges / 3. Enter "Character data" in Miscellaneous Charge amount field & / unlimited data in Miscellaneous Charge fields / 5. Click on add Miscellaneous Charge button. Observe the data is getting saved.	TS023_TC001
	Admin	Enhancement			Demand Note Automation || Login as Admin || Settings || Licence Fees || add Licences Fee || Licences Fee amount & Licence Fee Text / input fields are not working properly	1. Licence Fee Text is taking unlimited Data / 2. Licence Fee Amount filed Input characters	It should work	Go to "http://202.191.121.20/devtest/btrc" / 1. Log in as admin / 2. Go to Setting / 2. Click on Licence Fees / 3. Chick on add Licence Fee Button / 3. Enter "Character data" in Licence Fee amount & / unlimited data in Licence Fee text fields / 5. Click on add Update Licence fee button. Observe the data is getting saved.	TS024_TC006
	Admin	Enhancement			Demand Note Automation || Login as Admin || Settings || Licence Fees || Licences Fee Table Action Column edit button || Licences Fee amount & Licence Fee Text / input fields are not working properly	1. Licence Fee Text is taking unlimited Data / 2. Licence Fee Amount filed Input characters	It should work	Go to "http://202.191.121.20/devtest/btrc" / 1. Log in as admin / 2. Go to Setting / 2. Click on Licence Fees / 3. Click on action cloumn edit Button / 3. Enter "Character data" in Licence Fee Text field & / unlimited data in Licence Fee Amount fields / 5. Click on add Update Licence fee button. Observe the data is getting saved.	TS025_TC001
	Admin	Normal			Demand Note Automation || Login as Company|| Dashboard|| / Action || View||printing format is not working	1. printing format is not working	It should work	Go to "http://202.191.121.20/devtest/btrc" / 1. Log in as Company / 2. Go to Dashboard page / 3. Go to action Columm / 3. Click on print button and verify application / is not downloading printing format.	TS039_TC006

## Review_Comment
SL No	Document name	Section name	Review Comment	Author name	Solution	Review Comment	Reviewed By	Reviewed Date	Status